## Sheet1
OAC Meeting Agenda
1. | Review previous OAC meeting minutes
2. | Project Schedule
| A. | Critical Path Activities
| B. | Delays and Justifications
| C. | Recovery Schedule
| D. | Notice to Cure (if applicable)
| E. | 2-3 Week Look Ahead
| F. | Upcoming Inspections and Testing
3. | RFIs and Submittals Log
| A. | Procurement and Materials
4. | ASIs and Open Change Order Requests
5. | Allowances Log
6. | Change Orders
| A. | Additional Days, Calculation of Weather Days
7. | Pay Applications
| A. | Schedule of Values review
| B. | Percentage Completion, Progress Schedule
8. | Job Site Logistics (Access, Site Use, Temporary Facilities, Deliveries, Cleaning, Safety Plans)
9. | Field Observations and Deficiencies Log
10. | Review Date and Time of next OAC Meeting
11. | Site Visit after meeting
OAC Responsibility Matrix
AGENDA ITEM |  |  | OWNER | ARCHITECT |  | CONTRACTOR
1. | Review previous OAC meeting minutes |  | C | A | R | C
2. | Project Schedule |  | I | A |  | R
| A. | Critical Path Activities review | I | A |  | R
| B. | Delays and Justifications | C | A |  | R
| C. | Recovery Schedule | I | A |  | R
| D. | Notice to Cure (if applicable) | A | R |  | C
| E. | 2-3 Week Look Ahead | C | A |  | R
| F. | Upcoming Inspections and Testing | C | A |  | R
3. | RFIs and Submittals Log |  | C | A |  | R
| A. | Procurement and Materials | I | A |  | R
4. | ASIs and Open Change Order Requests |  | C | A | R | C
5. | Allowances Log |  | C | A | R | C
6. | Change Orders |  | C | A |  | R
| A. | Additional Days, Weather Days | C | A |  | R
7. | Pay Applications |  | C | A |  | R
| A. | Schedule of Values review | C | A |  | R
| B. | Percentage Completion, Progress Schedule | C | A |  | R
8. | Job Site Logistics |  | C | A |  | R
9. | Field Observations and Deficiencies Log |  | C | A | R | C
10. | Review Date and Time of next OAC Meeting |  | C | A | R | C
11. | Site Visit |  | C | A | R | R
R | Responsible. The person (or people) actually completing the work.
A | Accountable. The person that must answer for and/or sign off on the deliverable.
C | Consulted. Those that provide input based on how the deliverable will affect their domain.
I | Informed. Those that need to be kept in the loop on the project progress.